## Dashboard
Construction Project Controls Analytics Dashboard
Synthetic construction dataset for Excel, SQL, Access, and Power BI portfolio practice
Metric | Value |  | Project | Budget | Actual Cost | Variance | Risk Flag
Total Baseline Budget | 32025000 |  | Fab Tool Install - North Bay | 8350000 | 9492224.53 | -1142224.53 | Over Budget
Total Planned Cost | 33295966.71 |  | Cleanroom Expansion Phase 2 | 12600000 | 14012584.42 | -1412584.42 | Over Budget
Total Actual Cost | 35989940.52 |  | Utility Yard Upgrade | 4925000 | 5988441.5 | -1063441.5 | Over Budget
Cost Variance | -2693973.81 |  | Process Piping Retrofit | 6150000 | 6496690.07 | -346690.07 | Over Budget
Total Planned Hours | 302480
Total Actual Hours | 329284
Discipline | Planned Cost | Actual Cost | Planned Hours | Actual Hours
Civil | 5884453.76 | 6172776.01 | 53252 | 58762
Structural | 5396918.47 | 6121468.51 | 49529 | 58271
Mechanical | 5446563.19 | 5809038.91 | 49945 | 54146
Electrical | 5537305.85 | 5929759.88 | 50480 | 54087
Instrumentation | 5568467.77 | 6184577.04 | 51519 | 55846
Commissioning | 5462257.67 | 5772320.17 | 47755 | 48172

## Projects
project_id | project_name | location | project_type | status | start_date | planned_finish_date | baseline_budget
P1001 | Fab Tool Install - North Bay | Chandler AZ | Semiconductor | Active | 2025-01-06 | 2025-09-26 | 8350000
P1002 | Cleanroom Expansion Phase 2 | Chandler AZ | Semiconductor | Active | 2025-02-03 | 2025-11-14 | 12600000
P1003 | Utility Yard Upgrade | Mesa AZ | Industrial | At Risk | 2025-01-20 | 2025-08-22 | 4925000
P1004 | Process Piping Retrofit | Phoenix AZ | Manufacturing | Active | 2025-03-03 | 2025-10-31 | 6150000

## Schedule
task_id | project_id | task_name | discipline | planned_start | planned_finish | actual_finish | percent_complete | task_status
P1001-T01 | P1001 | Civil Phase 1 | Civil | 2025-01-09 | 2025-01-28 |  | 0.38 | Not Started
P1001-T02 | P1001 | Civil Phase 2 | Civil | 2025-02-12 | 2025-03-23 | 2025-03-23 | 1 | Complete
P1001-T03 | P1001 | Civil Phase 3 | Civil | 2025-03-04 | 2025-04-08 |  | 0.71 | Not Started
P1001-T04 | P1001 | Civil Phase 4 | Civil | 2025-04-09 | 2025-05-03 |  | 0.47 | Delayed
P1001-T05 | P1001 | Civil Phase 5 | Civil | 2025-05-08 | 2025-05-29 | 2025-06-01 | 1 | Complete
P1001-T06 | P1001 | Structural Phase 1 | Structural | 2025-01-17 | 2025-02-15 | 2025-02-20 | 1 | Complete
P1001-T07 | P1001 | Structural Phase 2 | Structural | 2025-02-11 | 2025-03-10 |  | 0.25 | Not Started
P1001-T08 | P1001 | Structural Phase 3 | Structural | 2025-03-13 | 2025-04-01 |  | 0.36 | In Progress
P1001-T09 | P1001 | Structural Phase 4 | Structural | 2025-04-03 | 2025-04-30 | 2025-05-06 | 1 | Complete
P1001-T10 | P1001 | Structural Phase 5 | Structural | 2025-04-29 | 2025-05-21 |  | 0.24 | Delayed
P1001-T11 | P1001 | Mechanical Phase 1 | Mechanical | 2025-01-08 | 2025-02-18 |  | 0.33 | Not Started
P1001-T12 | P1001 | Mechanical Phase 2 | Mechanical | 2025-02-05 | 2025-03-07 |  | 0.28 | Not Started
P1001-T13 | P1001 | Mechanical Phase 3 | Mechanical | 2025-03-10 | 2025-04-05 | 2025-04-11 | 1 | Complete
P1001-T14 | P1001 | Mechanical Phase 4 | Mechanical | 2025-04-07 | 2025-04-26 |  | 0.46 | Delayed
P1001-T15 | P1001 | Mechanical Phase 5 | Mechanical | 2025-05-01 | 2025-06-09 | 2025-06-11 | 1 | Complete
P1001-T16 | P1001 | Electrical Phase 1 | Electrical | 2025-01-10 | 2025-02-18 | 2025-02-21 | 1 | Complete
P1001-T17 | P1001 | Electrical Phase 2 | Electrical | 2025-02-05 | 2025-03-14 |  | 0.27 | In Progress
P1001-T18 | P1001 | Electrical Phase 3 | Electrical | 2025-03-10 | 2025-04-06 | 2025-04-09 | 1 | Complete
P1001-T19 | P1001 | Electrical Phase 4 | Electrical | 2025-03-31 | 2025-04-25 |  | 0.66 | In Progress
P1001-T20 | P1001 | Electrical Phase 5 | Electrical | 2025-05-05 | 2025-06-15 |  | 0.64 | In Progress
P1001-T21 | P1001 | Instrumentation Phase 1 | Instrumentation | 2025-01-17 | 2025-02-14 |  | 0.25 | In Progress
P1001-T22 | P1001 | Instrumentation Phase 2 | Instrumentation | 2025-02-06 | 2025-03-02 | 2025-03-02 | 1 | Complete
P1001-T23 | P1001 | Instrumentation Phase 3 | Instrumentation | 2025-03-11 | 2025-04-07 |  | 0.85 | Delayed
P1001-T24 | P1001 | Instrumentation Phase 4 | Instrumentation | 2025-04-08 | 2025-05-08 |  | 0.78 | In Progress
P1001-T25 | P1001 | Instrumentation Phase 5 | Instrumentation | 2025-05-07 | 2025-06-10 |  | 0.65 | Delayed
P1001-T26 | P1001 | Commissioning Phase 1 | Commissioning | 2025-01-17 | 2025-02-17 | 2025-02-20 | 1 | Complete
P1001-T27 | P1001 | Commissioning Phase 2 | Commissioning | 2025-02-11 | 2025-03-17 | 2025-03-17 | 1 | Complete
P1001-T28 | P1001 | Commissioning Phase 3 | Commissioning | 2025-03-03 | 2025-03-31 |  | 0.49 | Not Started
P1001-T29 | P1001 | Commissioning Phase 4 | Commissioning | 2025-03-31 | 2025-05-08 |  | 0.15 | In Progress
P1001-T30 | P1001 | Commissioning Phase 5 | Commissioning | 2025-05-07 | 2025-06-07 | 2025-06-09 | 1 | Complete
P1002-T01 | P1002 | Civil Phase 1 | Civil | 2025-02-05 | 2025-03-06 |  | 0.42 | Delayed
P1002-T02 | P1002 | Civil Phase 2 | Civil | 2025-03-09 | 2025-04-07 |  | 0.26 | Delayed
P1002-T03 | P1002 | Civil Phase 3 | Civil | 2025-04-02 | 2025-05-01 |  | 0.3 | Not Started
P1002-T04 | P1002 | Civil Phase 4 | Civil | 2025-05-08 | 2025-06-02 |  | 0.18 | Delayed
P1002-T05 | P1002 | Civil Phase 5 | Civil | 2025-05-30 | 2025-06-21 |  | 0.52 | Not Started
P1002-T06 | P1002 | Structural Phase 1 | Structural | 2025-02-11 | 2025-03-07 | 2025-03-07 | 1 | Complete
P1002-T07 | P1002 | Structural Phase 2 | Structural | 2025-03-04 | 2025-03-23 | 2025-03-27 | 1 | Complete
P1002-T08 | P1002 | Structural Phase 3 | Structural | 2025-04-07 | 2025-04-26 |  | 0.38 | In Progress
P1002-T09 | P1002 | Structural Phase 4 | Structural | 2025-05-09 | 2025-05-30 |  | 0.2 | Delayed
P1002-T10 | P1002 | Structural Phase 5 | Structural | 2025-05-31 | 2025-07-01 | 2025-07-06 | 1 | Complete
P1002-T11 | P1002 | Mechanical Phase 1 | Mechanical | 2025-02-10 | 2025-03-05 |  | 0.19 | Not Started
P1002-T12 | P1002 | Mechanical Phase 2 | Mechanical | 2025-03-08 | 2025-04-07 |  | 0.43 | Not Started
P1002-T13 | P1002 | Mechanical Phase 3 | Mechanical | 2025-04-04 | 2025-05-07 |  | 0.49 | Delayed
P1002-T14 | P1002 | Mechanical Phase 4 | Mechanical | 2025-05-05 | 2025-06-04 |  | 0.78 | Delayed
P1002-T15 | P1002 | Mechanical Phase 5 | Mechanical | 2025-06-04 | 2025-07-01 | 2025-07-01 | 1 | Complete
P1002-T16 | P1002 | Electrical Phase 1 | Electrical | 2025-02-04 | 2025-02-23 |  | 0.5 | Not Started
P1002-T17 | P1002 | Electrical Phase 2 | Electrical | 2025-03-14 | 2025-04-18 |  | 0.46 | In Progress
P1002-T18 | P1002 | Electrical Phase 3 | Electrical | 2025-04-07 | 2025-05-05 |  | 0.61 | Delayed
P1002-T19 | P1002 | Electrical Phase 4 | Electrical | 2025-05-05 | 2025-06-02 |  | 0.61 | In Progress
P1002-T20 | P1002 | Electrical Phase 5 | Electrical | 2025-05-28 | 2025-06-22 |  | 0.22 | Not Started
P1002-T21 | P1002 | Instrumentation Phase 1 | Instrumentation | 2025-02-08 | 2025-03-16 |  | 0.87 | Delayed
P1002-T22 | P1002 | Instrumentation Phase 2 | Instrumentation | 2025-03-06 | 2025-03-28 |  | 0.43 | Not Started
P1002-T23 | P1002 | Instrumentation Phase 3 | Instrumentation | 2025-04-05 | 2025-05-10 |  | 0.85 | Delayed
P1002-T24 | P1002 | Instrumentation Phase 4 | Instrumentation | 2025-04-28 | 2025-06-04 | 2025-06-06 | 1 | Complete
P1002-T25 | P1002 | Instrumentation Phase 5 | Instrumentation | 2025-05-26 | 2025-06-30 |  | 0.83 | Not Started
P1002-T26 | P1002 | Commissioning Phase 1 | Commissioning | 2025-02-04 | 2025-03-14 | 2025-03-18 | 1 | Complete
P1002-T27 | P1002 | Commissioning Phase 2 | Commissioning | 2025-03-03 | 2025-03-25 | 2025-03-28 | 1 | Complete
P1002-T28 | P1002 | Commissioning Phase 3 | Commissioning | 2025-04-03 | 2025-04-30 | 2025-05-05 | 1 | Complete
P1002-T29 | P1002 | Commissioning Phase 4 | Commissioning | 2025-05-06 | 2025-06-13 |  | 0.44 | Delayed
P1002-T30 | P1002 | Commissioning Phase 5 | Commissioning | 2025-06-04 | 2025-07-01 | 2025-07-02 | 1 | Complete
P1003-T01 | P1003 | Civil Phase 1 | Civil | 2025-01-25 | 2025-03-04 |  | 0.85 | Delayed
P1003-T02 | P1003 | Civil Phase 2 | Civil | 2025-02-28 | 2025-04-01 | 2025-04-01 | 1 | Complete
P1003-T03 | P1003 | Civil Phase 3 | Civil | 2025-03-23 | 2025-04-16 |  | 0.84 | Not Started
P1003-T04 | P1003 | Civil Phase 4 | Civil | 2025-04-20 | 2025-05-26 |  | 0.4 | Delayed
P1003-T05 | P1003 | Civil Phase 5 | Civil | 2025-05-20 | 2025-06-15 |  | 0.16 | In Progress
P1003-T06 | P1003 | Structural Phase 1 | Structural | 2025-01-24 | 2025-03-06 |  | 0.69 | Not Started
P1003-T07 | P1003 | Structural Phase 2 | Structural | 2025-02-21 | 2025-03-17 | 2025-03-18 | 1 | Complete
P1003-T08 | P1003 | Structural Phase 3 | Structural | 2025-03-22 | 2025-04-14 | 2025-04-27 | 1 | Complete
P1003-T09 | P1003 | Structural Phase 4 | Structural | 2025-04-20 | 2025-05-17 | 2025-05-18 | 1 | Complete
P1003-T10 | P1003 | Structural Phase 5 | Structural | 2025-05-12 | 2025-06-07 | 2025-06-12 | 1 | Complete
P1003-T11 | P1003 | Mechanical Phase 1 | Mechanical | 2025-01-20 | 2025-03-01 | 2025-03-16 | 1 | Complete
P1003-T12 | P1003 | Mechanical Phase 2 | Mechanical | 2025-02-20 | 2025-04-02 | 2025-04-02 | 1 | Complete
P1003-T13 | P1003 | Mechanical Phase 3 | Mechanical | 2025-03-20 | 2025-04-22 | 2025-05-03 | 1 | Complete
P1003-T14 | P1003 | Mechanical Phase 4 | Mechanical | 2025-04-19 | 2025-05-19 | 2025-05-23 | 1 | Complete
P1003-T15 | P1003 | Mechanical Phase 5 | Mechanical | 2025-05-21 | 2025-06-22 | 2025-06-24 | 1 | Complete
P1003-T16 | P1003 | Electrical Phase 1 | Electrical | 2025-01-25 | 2025-03-01 |  | 0.76 | In Progress
P1003-T17 | P1003 | Electrical Phase 2 | Electrical | 2025-02-24 | 2025-03-30 |  | 0.17 | In Progress
P1003-T18 | P1003 | Electrical Phase 3 | Electrical | 2025-03-18 | 2025-04-06 | 2025-04-16 | 1 | Complete
P1003-T19 | P1003 | Electrical Phase 4 | Electrical | 2025-04-14 | 2025-05-11 |  | 0.84 | In Progress
P1003-T20 | P1003 | Electrical Phase 5 | Electrical | 2025-05-21 | 2025-06-16 |  | 0.23 | Not Started
P1003-T21 | P1003 | Instrumentation Phase 1 | Instrumentation | 2025-01-23 | 2025-03-01 |  | 0.8 | Not Started
P1003-T22 | P1003 | Instrumentation Phase 2 | Instrumentation | 2025-02-25 | 2025-03-20 | 2025-04-03 | 1 | Complete
P1003-T23 | P1003 | Instrumentation Phase 3 | Instrumentation | 2025-03-28 | 2025-04-28 | 2025-04-29 | 1 | Complete
P1003-T24 | P1003 | Instrumentation Phase 4 | Instrumentation | 2025-04-23 | 2025-05-13 | 2025-05-30 | 1 | Complete
P1003-T25 | P1003 | Instrumentation Phase 5 | Instrumentation | 2025-05-23 | 2025-06-26 |  | 0.83 | Not Started
P1003-T26 | P1003 | Commissioning Phase 1 | Commissioning | 2025-01-25 | 2025-02-23 | 2025-03-09 | 1 | Complete
P1003-T27 | P1003 | Commissioning Phase 2 | Commissioning | 2025-02-22 | 2025-03-21 | 2025-03-26 | 1 | Complete
P1003-T28 | P1003 | Commissioning Phase 3 | Commissioning | 2025-03-28 | 2025-05-07 |  | 0.27 | In Progress
P1003-T29 | P1003 | Commissioning Phase 4 | Commissioning | 2025-04-18 | 2025-05-17 | 2025-06-03 | 1 | Complete
P1003-T30 | P1003 | Commissioning Phase 5 | Commissioning | 2025-05-15 | 2025-06-05 |  | 0.33 | Not Started
P1004-T01 | P1004 | Civil Phase 1 | Civil | 2025-03-14 | 2025-04-10 | 2025-04-16 | 1 | Complete
P1004-T02 | P1004 | Civil Phase 2 | Civil | 2025-04-08 | 2025-05-04 |  | 0.75 | In Progress
P1004-T03 | P1004 | Civil Phase 3 | Civil | 2025-05-03 | 2025-05-27 |  | 0.41 | In Progress
P1004-T04 | P1004 | Civil Phase 4 | Civil | 2025-06-05 | 2025-07-04 |  | 0.81 | In Progress
P1004-T05 | P1004 | Civil Phase 5 | Civil | 2025-07-01 | 2025-07-27 | 2025-08-03 | 1 | Complete
P1004-T06 | P1004 | Structural Phase 1 | Structural | 2025-03-03 | 2025-04-11 | 2025-04-18 | 1 | Complete
P1004-T07 | P1004 | Structural Phase 2 | Structural | 2025-04-05 | 2025-05-10 |  | 0.53 | Delayed
P1004-T08 | P1004 | Structural Phase 3 | Structural | 2025-05-02 | 2025-06-01 |  | 0.26 | Delayed
P1004-T09 | P1004 | Structural Phase 4 | Structural | 2025-05-31 | 2025-07-05 |  | 0.49 | Delayed
P1004-T10 | P1004 | Structural Phase 5 | Structural | 2025-06-23 | 2025-07-27 |  | 0.58 | In Progress
P1004-T11 | P1004 | Mechanical Phase 1 | Mechanical | 2025-03-08 | 2025-04-10 |  | 0.83 | In Progress
P1004-T12 | P1004 | Mechanical Phase 2 | Mechanical | 2025-04-09 | 2025-05-17 | 2025-05-21 | 1 | Complete
P1004-T13 | P1004 | Mechanical Phase 3 | Mechanical | 2025-05-06 | 2025-06-14 | 2025-06-20 | 1 | Complete
P1004-T14 | P1004 | Mechanical Phase 4 | Mechanical | 2025-05-29 | 2025-06-26 |  | 0.74 | In Progress
P1004-T15 | P1004 | Mechanical Phase 5 | Mechanical | 2025-07-02 | 2025-08-08 |  | 0.19 | In Progress
P1004-T16 | P1004 | Electrical Phase 1 | Electrical | 2025-03-14 | 2025-04-18 | 2025-04-23 | 1 | Complete
P1004-T17 | P1004 | Electrical Phase 2 | Electrical | 2025-04-06 | 2025-05-17 |  | 0.39 | In Progress
P1004-T18 | P1004 | Electrical Phase 3 | Electrical | 2025-05-09 | 2025-06-08 |  | 0.38 | Delayed
P1004-T19 | P1004 | Electrical Phase 4 | Electrical | 2025-05-27 | 2025-06-25 | 2025-06-29 | 1 | Complete
P1004-T20 | P1004 | Electrical Phase 5 | Electrical | 2025-06-30 | 2025-08-10 |  | 0.77 | In Progress
P1004-T21 | P1004 | Instrumentation Phase 1 | Instrumentation | 2025-03-07 | 2025-03-29 |  | 0.46 | Delayed
P1004-T22 | P1004 | Instrumentation Phase 2 | Instrumentation | 2025-04-10 | 2025-05-19 |  | 0.7 | In Progress
P1004-T23 | P1004 | Instrumentation Phase 3 | Instrumentation | 2025-05-01 | 2025-06-11 | 2025-06-11 | 1 | Complete
P1004-T24 | P1004 | Instrumentation Phase 4 | Instrumentation | 2025-05-27 | 2025-06-25 |  | 0.63 | In Progress
P1004-T25 | P1004 | Instrumentation Phase 5 | Instrumentation | 2025-07-04 | 2025-08-14 | 2025-08-16 | 1 | Complete
P1004-T26 | P1004 | Commissioning Phase 1 | Commissioning | 2025-03-06 | 2025-03-28 | 2025-03-31 | 1 | Complete
P1004-T27 | P1004 | Commissioning Phase 2 | Commissioning | 2025-04-05 | 2025-05-12 | 2025-05-16 | 1 | Complete
P1004-T28 | P1004 | Commissioning Phase 3 | Commissioning | 2025-04-30 | 2025-06-04 |  | 0.58 | Not Started
P1004-T29 | P1004 | Commissioning Phase 4 | Commissioning | 2025-06-01 | 2025-07-01 |  | 0.72 | Not Started
P1004-T30 | P1004 | Commissioning Phase 5 | Commissioning | 2025-06-24 | 2025-07-25 | 2025-07-27 | 1 | Complete

## Cost
project_id | task_id | cost_category | planned_cost | actual_cost | cost_variance
P1001 | P1001-T01 | Civil | 320975.34 | 326388.46 | -5413.12
P1001 | P1001-T02 | Civil | 386345.64 | 345179.96 | 41165.68
P1001 | P1001-T03 | Civil | 380646.8 | 500730.36 | -120083.56
P1001 | P1001-T04 | Civil | 275701.91 | 268648.91 | 7053
P1001 | P1001-T05 | Civil | 298841.96 | 353855.12 | -55013.16
P1001 | P1001-T06 | Structural | 250701.82 | 235372.82 | 15329
P1001 | P1001-T07 | Structural | 334930.12 | 356141.24 | -21211.12
P1001 | P1001-T08 | Structural | 233250.21 | 207849.67 | 25400.54
P1001 | P1001-T09 | Structural | 278242.01 | 300564.41 | -22322.4
P1001 | P1001-T10 | Structural | 183945.24 | 198251 | -14305.76
P1001 | P1001-T11 | Mechanical | 342831.17 | 409323.33 | -66492.16
P1001 | P1001-T12 | Mechanical | 302550.95 | 307750.69 | -5199.74
P1001 | P1001-T13 | Mechanical | 357950.09 | 398958.92 | -41008.83
P1001 | P1001-T14 | Mechanical | 335614.96 | 320557.66 | 15057.3
P1001 | P1001-T15 | Mechanical | 246284.36 | 254444.66 | -8160.3
P1001 | P1001-T16 | Electrical | 261736.88 | 257213.03 | 4523.85
P1001 | P1001-T17 | Electrical | 290700.85 | 296380.2 | -5679.35
P1001 | P1001-T18 | Electrical | 299065.77 | 301299.14 | -2233.37
P1001 | P1001-T19 | Electrical | 282824.8 | 320084.22 | -37259.42
P1001 | P1001-T20 | Electrical | 331064.61 | 399991.85 | -68927.24
P1001 | P1001-T21 | Instrumentation | 216207.89 | 225136.81 | -8928.92
P1001 | P1001-T22 | Instrumentation | 372491.24 | 361826.99 | 10664.25
P1001 | P1001-T23 | Instrumentation | 328423.02 | 342151.75 | -13728.73
P1001 | P1001-T24 | Instrumentation | 183133.62 | 227067.95 | -43934.33
P1001 | P1001-T25 | Instrumentation | 312432.04 | 398302.44 | -85870.4
P1001 | P1001-T26 | Commissioning | 347097.87 | 354980.62 | -7882.75
P1001 | P1001-T27 | Commissioning | 372195.42 | 397485.62 | -25290.2
P1001 | P1001-T28 | Commissioning | 367084.51 | 351543.15 | 15541.36
P1001 | P1001-T29 | Commissioning | 245355.65 | 207524.77 | 37830.88
P1001 | P1001-T30 | Commissioning | 306931.9 | 267218.78 | 39713.12
P1002 | P1002-T01 | Civil | 542159.64 | 550394.69 | -8235.05
P1002 | P1002-T02 | Civil | 285952.73 | 261092.34 | 24860.39
P1002 | P1002-T03 | Civil | 502926.53 | 557107.09 | -54180.56
P1002 | P1002-T04 | Civil | 565574.34 | 614861.06 | -49286.72
P1002 | P1002-T05 | Civil | 556694.8 | 512514.98 | 44179.82
P1002 | P1002-T06 | Structural | 315759.54 | 336924.37 | -21164.83
P1002 | P1002-T07 | Structural | 530836.93 | 664819.24 | -133982.31
P1002 | P1002-T08 | Structural | 559194.46 | 718776.53 | -159582.07
P1002 | P1002-T09 | Structural | 315143.56 | 363680.85 | -48537.29
P1002 | P1002-T10 | Structural | 458391.38 | 521739.75 | -63348.37
P1002 | P1002-T11 | Mechanical | 575013 | 571438.64 | 3574.36
P1002 | P1002-T12 | Mechanical | 456195.88 | 409126.14 | 47069.74
P1002 | P1002-T13 | Mechanical | 322778.1 | 435889.16 | -113111.06
P1002 | P1002-T14 | Mechanical | 367904.03 | 444178.79 | -76274.76
P1002 | P1002-T15 | Mechanical | 447623.07 | 499271.08 | -51648.01
P1002 | P1002-T16 | Electrical | 325081.95 | 273118.95 | 51963
P1002 | P1002-T17 | Electrical | 367977.75 | 371974.4 | -3996.65
P1002 | P1002-T18 | Electrical | 511040.9 | 563879.74 | -52838.84
P1002 | P1002-T19 | Electrical | 368326.19 | 394375.66 | -26049.47
P1002 | P1002-T20 | Electrical | 475587.67 | 467981.86 | 7605.81
P1002 | P1002-T21 | Instrumentation | 472056.64 | 545804.5 | -73747.86
P1002 | P1002-T22 | Instrumentation | 420295.23 | 487552.5 | -67257.27
P1002 | P1002-T23 | Instrumentation | 347463.04 | 340049.69 | 7413.35
P1002 | P1002-T24 | Instrumentation | 540400.2 | 470870.38 | 69529.82
P1002 | P1002-T25 | Instrumentation | 406227.74 | 368466.43 | 37761.31
P1002 | P1002-T26 | Commissioning | 368553.89 | 446058.68 | -77504.79
P1002 | P1002-T27 | Commissioning | 581182.71 | 576478.72 | 4703.99
P1002 | P1002-T28 | Commissioning | 446655.65 | 506888.55 | -60232.9
P1002 | P1002-T29 | Commissioning | 274418.18 | 262739.6 | 11678.58
P1002 | P1002-T30 | Commissioning | 363925.43 | 474530.05 | -110604.62
P1003 | P1003-T01 | Civil | 150679.9 | 150688.17 | -8.27
P1003 | P1003-T02 | Civil | 120866.28 | 113334.43 | 7531.85
P1003 | P1003-T03 | Civil | 136258.26 | 140364.92 | -4106.66
P1003 | P1003-T04 | Civil | 201890.66 | 233525.85 | -31635.19
P1003 | P1003-T05 | Civil | 208692.07 | 271394.05 | -62701.98
P1003 | P1003-T06 | Structural | 173582.12 | 232153.63 | -58571.51
P1003 | P1003-T07 | Structural | 210038.93 | 175807.92 | 34231.01
P1003 | P1003-T08 | Structural | 180573.23 | 224523.62 | -43950.39
P1003 | P1003-T09 | Structural | 202706.87 | 172257.94 | 30448.93
P1003 | P1003-T10 | Structural | 167644.47 | 227171.43 | -59526.96
P1003 | P1003-T11 | Mechanical | 176703.83 | 192730.78 | -16026.95
P1003 | P1003-T12 | Mechanical | 163134.43 | 193112.97 | -29978.54
P1003 | P1003-T13 | Mechanical | 153944.13 | 157378.96 | -3434.83
P1003 | P1003-T14 | Mechanical | 109917.52 | 102210.64 | 7706.88
P1003 | P1003-T15 | Mechanical | 220813.16 | 259020.21 | -38207.05
P1003 | P1003-T16 | Electrical | 203186.58 | 188511.45 | 14675.13
P1003 | P1003-T17 | Electrical | 208275.94 | 195911 | 12364.94
P1003 | P1003-T18 | Electrical | 228414.98 | 273171.69 | -44756.71
P1003 | P1003-T19 | Electrical | 184196.5 | 206346.79 | -22150.29
P1003 | P1003-T20 | Electrical | 212892.84 | 306266.36 | -93373.52
P1003 | P1003-T21 | Instrumentation | 201149.86 | 257671.25 | -56521.39
P1003 | P1003-T22 | Instrumentation | 111075.51 | 162167.21 | -51091.7
P1003 | P1003-T23 | Instrumentation | 182414.89 | 238752.98 | -56338.09
P1003 | P1003-T24 | Instrumentation | 212427.43 | 217899.5 | -5472.07
P1003 | P1003-T25 | Instrumentation | 205288.94 | 297344.11 | -92055.17
P1003 | P1003-T26 | Commissioning | 185396.19 | 194883.56 | -9487.37
P1003 | P1003-T27 | Commissioning | 110178.7 | 101604.31 | 8574.39
P1003 | P1003-T28 | Commissioning | 109193.49 | 91952.27 | 17241.22
P1003 | P1003-T29 | Commissioning | 217210.34 | 235049.13 | -17838.79
P1003 | P1003-T30 | Commissioning | 179808.13 | 175234.37 | 4573.76
P1004 | P1004-T01 | Civil | 186753.49 | 216637.51 | -29884.02
P1004 | P1004-T02 | Civil | 141222.98 | 134803.19 | 6419.79
P1004 | P1004-T03 | Civil | 224342.99 | 220615.39 | 3727.6
P1004 | P1004-T04 | Civil | 134185.87 | 122083.45 | 12102.42
P1004 | P1004-T05 | Civil | 263741.57 | 278556.08 | -14814.51
P1004 | P1004-T06 | Structural | 186982.33 | 173205.36 | 13776.97
P1004 | P1004-T07 | Structural | 255818.97 | 320536.98 | -64718.01
P1004 | P1004-T08 | Structural | 187520.25 | 224939.65 | -37419.4
P1004 | P1004-T09 | Structural | 152545.85 | 178964.14 | -26418.29
P1004 | P1004-T10 | Structural | 219110.18 | 287787.96 | -68677.78
P1004 | P1004-T11 | Mechanical | 144143.53 | 156998.21 | -12854.68
P1004 | P1004-T12 | Mechanical | 155059.65 | 168727.96 | -13668.31
P1004 | P1004-T13 | Mechanical | 211955.97 | 204367.66 | 7588.31
P1004 | P1004-T14 | Mechanical | 207457.7 | 190355.66 | 17102.04
P1004 | P1004-T15 | Mechanical | 148687.66 | 133196.79 | 15490.87
P1004 | P1004-T16 | Electrical | 258159.24 | 231342.21 | 26817.03
P1004 | P1004-T17 | Electrical | 157348.41 | 205631.99 | -48283.58
P1004 | P1004-T18 | Electrical | 135810.22 | 159769.23 | -23959.01
P1004 | P1004-T19 | Electrical | 183853.3 | 213216.89 | -29363.59
P1004 | P1004-T20 | Electrical | 251760.47 | 303293.22 | -51532.75
P1004 | P1004-T21 | Instrumentation | 171116.04 | 209680.15 | -38564.11
P1004 | P1004-T22 | Instrumentation | 245602.63 | 324717.29 | -79114.66
P1004 | P1004-T23 | Instrumentation | 220375.52 | 256144.96 | -35769.44
P1004 | P1004-T24 | Instrumentation | 226606.38 | 212645.83 | 13960.55
P1004 | P1004-T25 | Instrumentation | 193279.91 | 240324.32 | -47044.41
P1004 | P1004-T26 | Commissioning | 135140.42 | 135609.5 | -469.08
P1004 | P1004-T27 | Commissioning | 174752.32 | 218452.68 | -43700.36
P1004 | P1004-T28 | Commissioning | 250840.57 | 316955 | -66114.43
P1004 | P1004-T29 | Commissioning | 191340.5 | 210515.15 | -19174.65
P1004 | P1004-T30 | Commissioning | 234995.8 | 246615.66 | -11619.86

## Resources
project_id | task_id | discipline | planned_hours | actual_hours | hour_variance
P1001 | P1001-T01 | Civil | 2583 | 3127 | 544
P1001 | P1001-T02 | Civil | 3919 | 3229 | -690
P1001 | P1001-T03 | Civil | 3281 | 4375 | 1094
P1001 | P1001-T04 | Civil | 2948 | 3230 | 282
P1001 | P1001-T05 | Civil | 2999 | 3623 | 624
P1001 | P1001-T06 | Structural | 2619 | 2938 | 319
P1001 | P1001-T07 | Structural | 2609 | 2592 | -17
P1001 | P1001-T08 | Structural | 2062 | 2204 | 142
P1001 | P1001-T09 | Structural | 2582 | 2576 | -6
P1001 | P1001-T10 | Structural | 1618 | 2017 | 399
P1001 | P1001-T11 | Mechanical | 3086 | 3515 | 429
P1001 | P1001-T12 | Mechanical | 2888 | 3248 | 360
P1001 | P1001-T13 | Mechanical | 3325 | 4128 | 803
P1001 | P1001-T14 | Mechanical | 3572 | 4532 | 960
P1001 | P1001-T15 | Mechanical | 1972 | 2315 | 343
P1001 | P1001-T16 | Electrical | 2307 | 2315 | 8
P1001 | P1001-T17 | Electrical | 2589 | 3195 | 606
P1001 | P1001-T18 | Electrical | 2684 | 2893 | 209
P1001 | P1001-T19 | Electrical | 2371 | 2213 | -158
P1001 | P1001-T20 | Electrical | 3153 | 3640 | 487
P1001 | P1001-T21 | Instrumentation | 2096 | 2288 | 192
P1001 | P1001-T22 | Instrumentation | 3875 | 3508 | -367
P1001 | P1001-T23 | Instrumentation | 3391 | 4582 | 1191
P1001 | P1001-T24 | Instrumentation | 1783 | 2435 | 652
P1001 | P1001-T25 | Instrumentation | 3173 | 3962 | 789
P1001 | P1001-T26 | Commissioning | 2712 | 3022 | 310
P1001 | P1001-T27 | Commissioning | 2951 | 2472 | -479
P1001 | P1001-T28 | Commissioning | 2969 | 2421 | -548
P1001 | P1001-T29 | Commissioning | 1904 | 2166 | 262
P1001 | P1001-T30 | Commissioning | 3196 | 4320 | 1124
P1002 | P1002-T01 | Civil | 4408 | 5506 | 1098
P1002 | P1002-T02 | Civil | 2993 | 2766 | -227
P1002 | P1002-T03 | Civil | 5112 | 4642 | -470
P1002 | P1002-T04 | Civil | 5443 | 7353 | 1910
P1002 | P1002-T05 | Civil | 4640 | 5213 | 573
P1002 | P1002-T06 | Structural | 2555 | 3139 | 584
P1002 | P1002-T07 | Structural | 4594 | 6087 | 1493
P1002 | P1002-T08 | Structural | 6032 | 7555 | 1523
P1002 | P1002-T09 | Structural | 3135 | 3428 | 293
P1002 | P1002-T10 | Structural | 3694 | 4817 | 1123
P1002 | P1002-T11 | Mechanical | 5364 | 4935 | -429
P1002 | P1002-T12 | Mechanical | 4265 | 3973 | -292
P1002 | P1002-T13 | Mechanical | 2937 | 2765 | -172
P1002 | P1002-T14 | Mechanical | 2859 | 2595 | -264
P1002 | P1002-T15 | Mechanical | 4202 | 3767 | -435
P1002 | P1002-T16 | Electrical | 2558 | 2140 | -418
P1002 | P1002-T17 | Electrical | 2893 | 2647 | -246
P1002 | P1002-T18 | Electrical | 4843 | 5945 | 1102
P1002 | P1002-T19 | Electrical | 3088 | 2723 | -365
P1002 | P1002-T20 | Electrical | 4932 | 5445 | 513
P1002 | P1002-T21 | Instrumentation | 3883 | 4135 | 252
P1002 | P1002-T22 | Instrumentation | 4213 | 4270 | 57
P1002 | P1002-T23 | Instrumentation | 2883 | 3782 | 899
P1002 | P1002-T24 | Instrumentation | 4455 | 4000 | -455
P1002 | P1002-T25 | Instrumentation | 3637 | 3048 | -589
P1002 | P1002-T26 | Commissioning | 3282 | 3328 | 46
P1002 | P1002-T27 | Commissioning | 4479 | 4130 | -349
P1002 | P1002-T28 | Commissioning | 4044 | 3516 | -528
P1002 | P1002-T29 | Commissioning | 2632 | 2659 | 27
P1002 | P1002-T30 | Commissioning | 3544 | 3393 | -151
P1003 | P1003-T01 | Civil | 1189 | 1213 | 24
P1003 | P1003-T02 | Civil | 1048 | 871 | -177
P1003 | P1003-T03 | Civil | 1134 | 1081 | -53
P1003 | P1003-T04 | Civil | 1724 | 1659 | -65
P1003 | P1003-T05 | Civil | 1642 | 1744 | 102
P1003 | P1003-T06 | Structural | 1774 | 1946 | 172
P1003 | P1003-T07 | Structural | 2108 | 2384 | 276
P1003 | P1003-T08 | Structural | 1610 | 2343 | 733
P1003 | P1003-T09 | Structural | 1667 | 1927 | 260
P1003 | P1003-T10 | Structural | 1748 | 1914 | 166
P1003 | P1003-T11 | Mechanical | 1368 | 1539 | 171
P1003 | P1003-T12 | Mechanical | 1284 | 1096 | -188
P1003 | P1003-T13 | Mechanical | 1594 | 2113 | 519
P1003 | P1003-T14 | Mechanical | 977 | 1295 | 318
P1003 | P1003-T15 | Mechanical | 2362 | 2822 | 460
P1003 | P1003-T16 | Electrical | 2194 | 2526 | 332
P1003 | P1003-T17 | Electrical | 1932 | 2195 | 263
P1003 | P1003-T18 | Electrical | 1779 | 2108 | 329
P1003 | P1003-T19 | Electrical | 1675 | 1805 | 130
P1003 | P1003-T20 | Electrical | 1854 | 2218 | 364
P1003 | P1003-T21 | Instrumentation | 1642 | 1709 | 67
P1003 | P1003-T22 | Instrumentation | 1110 | 1667 | 557
P1003 | P1003-T23 | Instrumentation | 1870 | 1864 | -6
P1003 | P1003-T24 | Instrumentation | 2164 | 2692 | 528
P1003 | P1003-T25 | Instrumentation | 1967 | 2641 | 674
P1003 | P1003-T26 | Commissioning | 1746 | 2185 | 439
P1003 | P1003-T27 | Commissioning | 973 | 1237 | 264
P1003 | P1003-T28 | Commissioning | 881 | 787 | -94
P1003 | P1003-T29 | Commissioning | 1684 | 1905 | 221
P1003 | P1003-T30 | Commissioning | 1596 | 1504 | -92
P1004 | P1004-T01 | Civil | 1466 | 1397 | -69
P1004 | P1004-T02 | Civil | 1113 | 996 | -117
P1004 | P1004-T03 | Civil | 1756 | 1829 | 73
P1004 | P1004-T04 | Civil | 1269 | 1471 | 202
P1004 | P1004-T05 | Civil | 2585 | 3437 | 852
P1004 | P1004-T06 | Structural | 1781 | 2237 | 456
P1004 | P1004-T07 | Structural | 2461 | 2691 | 230
P1004 | P1004-T08 | Structural | 1683 | 1737 | 54
P1004 | P1004-T09 | Structural | 1456 | 1853 | 397
P1004 | P1004-T10 | Structural | 1741 | 1886 | 145
P1004 | P1004-T11 | Mechanical | 1269 | 1321 | 52
P1004 | P1004-T12 | Mechanical | 1310 | 1393 | 83
P1004 | P1004-T13 | Mechanical | 1765 | 2270 | 505
P1004 | P1004-T14 | Mechanical | 2064 | 2570 | 506
P1004 | P1004-T15 | Mechanical | 1482 | 1954 | 472
P1004 | P1004-T16 | Electrical | 2663 | 2746 | 83
P1004 | P1004-T17 | Electrical | 1422 | 1519 | 97
P1004 | P1004-T18 | Electrical | 1311 | 1684 | 373
P1004 | P1004-T19 | Electrical | 1597 | 1770 | 173
P1004 | P1004-T20 | Electrical | 2635 | 2360 | -275
P1004 | P1004-T21 | Instrumentation | 1423 | 1545 | 122
P1004 | P1004-T22 | Instrumentation | 1982 | 1951 | -31
P1004 | P1004-T23 | Instrumentation | 1891 | 1664 | -227
P1004 | P1004-T24 | Instrumentation | 2243 | 2516 | 273
P1004 | P1004-T25 | Instrumentation | 1838 | 1587 | -251
P1004 | P1004-T26 | Commissioning | 1435 | 1741 | 306
P1004 | P1004-T27 | Commissioning | 1450 | 1616 | 166
P1004 | P1004-T28 | Commissioning | 1930 | 1731 | -199
P1004 | P1004-T29 | Commissioning | 1946 | 2009 | 63
P1004 | P1004-T30 | Commissioning | 2401 | 2030 | -371

## Procurement
po_id | project_id | task_id | vendor | discipline | po_value | committed_cost | need_by_date | expected_delivery_date | delivery_status
P1001-PO001 | P1001 | P1001-T01 | Apex Mechanical | Civil | 237846.27 | 210424.37 | 2025-01-17 | 2025-02-02 | Late Risk
P1001-PO002 | P1001 | P1001-T02 | Sonoran Controls | Civil | 158474.46 | 140993.22 | 2025-02-20 | 2025-02-25 | Late Risk
P1001-PO003 | P1001 | P1001-T03 | Mesa Steel | Civil | 266771.07 | 288762.43 | 2025-03-12 | 2025-03-17 | Late Risk
P1001-PO006 | P1001 | P1001-T06 | Mesa Steel | Structural | 125740.1 | 99400.12 | 2025-01-25 | 2025-02-08 | Late Risk
P1001-PO007 | P1001 | P1001-T07 | Copperline Electric | Structural | 128325.04 | 109381.1 | 2025-02-19 | 2025-02-26 | Late Risk
P1001-PO008 | P1001 | P1001-T08 | Mesa Steel | Structural | 127380.09 | 112269.33 | 2025-03-21 | 2025-03-25 | Late Risk
P1001-PO011 | P1001 | P1001-T11 | Valley Civil | Mechanical | 162071.06 | 125727.07 | 2025-01-16 | 2025-01-29 | Late Risk
P1001-PO012 | P1001 | P1001-T12 | Copperline Electric | Mechanical | 123918.86 | 132640.91 | 2025-02-13 | 2025-02-19 | Late Risk
P1001-PO013 | P1001 | P1001-T13 | Mesa Steel | Mechanical | 176572.39 | 167529.73 | 2025-03-18 | 2025-03-22 | Late Risk
P1001-PO016 | P1001 | P1001-T16 | Copperline Electric | Electrical | 154473.6 | 123717.16 | 2025-01-18 | 2025-01-30 | Late Risk
P1001-PO017 | P1001 | P1001-T17 | Apex Mechanical | Electrical | 137032.76 | 149737.72 | 2025-02-13 | 2025-02-16 | Late Risk
P1001-PO018 | P1001 | P1001-T18 | Desert Safety Supply | Electrical | 204030.46 | 221238.42 | 2025-03-18 | 2025-03-23 | Late Risk
P1001-PO021 | P1001 | P1001-T21 | Mesa Steel | Instrumentation | 135163.01 | 146577.56 | 2025-01-25 | 2025-01-22 | On Track
P1001-PO022 | P1001 | P1001-T22 | Apex Mechanical | Instrumentation | 248245.34 | 262872.49 | 2025-02-14 | 2025-02-26 | Late Risk
P1001-PO023 | P1001 | P1001-T23 | Valley Civil | Instrumentation | 235659.8 | 235430.8 | 2025-03-19 | 2025-03-21 | Late Risk
P1001-PO026 | P1001 | P1001-T26 | Mesa Steel | Commissioning | 251657.57 | 200422.02 | 2025-01-25 | 2025-01-25 | On Track
P1001-PO027 | P1001 | P1001-T27 | Desert Safety Supply | Commissioning | 154153.99 | 142969.18 | 2025-02-19 | 2025-02-23 | Late Risk
P1001-PO028 | P1001 | P1001-T28 | Copperline Electric | Commissioning | 275896.2 | 279700.27 | 2025-03-11 | 2025-03-20 | Late Risk
P1002-PO001 | P1002 | P1002-T01 | Sonoran Controls | Civil | 421751.38 | 369689.94 | 2025-02-13 | 2025-02-19 | Late Risk
P1002-PO002 | P1002 | P1002-T02 | Desert Safety Supply | Civil | 171271.76 | 143624.51 | 2025-03-17 | 2025-03-14 | On Track
P1002-PO003 | P1002 | P1002-T03 | Apex Mechanical | Civil | 384628.42 | 339343.77 | 2025-04-10 | 2025-04-26 | Late Risk
P1002-PO006 | P1002 | P1002-T06 | Apex Mechanical | Structural | 149792.97 | 146259.4 | 2025-02-19 | 2025-02-20 | Late Risk
P1002-PO007 | P1002 | P1002-T07 | Desert Safety Supply | Structural | 188393.02 | 145489.39 | 2025-03-12 | 2025-03-12 | On Track
P1002-PO008 | P1002 | P1002-T08 | Copperline Electric | Structural | 353870.07 | 378503.75 | 2025-04-15 | 2025-04-21 | Late Risk
P1002-PO011 | P1002 | P1002-T11 | Desert Safety Supply | Mechanical | 249516.47 | 235679.7 | 2025-02-18 | 2025-02-27 | Late Risk
P1002-PO012 | P1002 | P1002-T12 | Mesa Steel | Mechanical | 273205.05 | 207895.28 | 2025-03-16 | 2025-03-20 | Late Risk
P1002-PO013 | P1002 | P1002-T13 | Desert Safety Supply | Mechanical | 133347.88 | 108895 | 2025-04-12 | 2025-04-10 | On Track
P1002-PO016 | P1002 | P1002-T16 | Copperline Electric | Electrical | 177729.02 | 134184.7 | 2025-02-12 | 2025-02-11 | On Track
P1002-PO017 | P1002 | P1002-T17 | Mesa Steel | Electrical | 129692.87 | 130763.22 | 2025-03-22 | 2025-03-20 | On Track
P1002-PO018 | P1002 | P1002-T18 | Sonoran Controls | Electrical | 201772.01 | 186077.57 | 2025-04-15 | 2025-04-16 | Late Risk
P1002-PO021 | P1002 | P1002-T21 | Mesa Steel | Instrumentation | 256393.13 | 248549.29 | 2025-02-16 | 2025-02-28 | Late Risk
P1002-PO022 | P1002 | P1002-T22 | Copperline Electric | Instrumentation | 175185.96 | 161838.71 | 2025-03-14 | 2025-03-28 | Late Risk
P1002-PO023 | P1002 | P1002-T23 | Sonoran Controls | Instrumentation | 211995.83 | 196003.7 | 2025-04-13 | 2025-04-26 | Late Risk
P1002-PO026 | P1002 | P1002-T26 | Mesa Steel | Commissioning | 133350.09 | 144336.76 | 2025-02-12 | 2025-02-16 | Late Risk
P1002-PO027 | P1002 | P1002-T27 | Copperline Electric | Commissioning | 434775.34 | 426814.31 | 2025-03-11 | 2025-03-27 | Late Risk
P1002-PO028 | P1002 | P1002-T28 | Desert Safety Supply | Commissioning | 279008.84 | 300059.82 | 2025-04-11 | 2025-04-21 | Late Risk
P1003-PO001 | P1003 | P1003-T01 | Sonoran Controls | Civil | 96728.86 | 94193.97 | 2025-02-02 | 2025-02-13 | Late Risk
P1003-PO002 | P1003 | P1003-T02 | Mesa Steel | Civil | 52738.52 | 52513.57 | 2025-03-08 | 2025-03-18 | Late Risk
P1003-PO003 | P1003 | P1003-T03 | Apex Mechanical | Civil | 108354.03 | 114703.66 | 2025-03-31 | 2025-04-02 | Late Risk
P1003-PO006 | P1003 | P1003-T06 | Apex Mechanical | Structural | 66203.17 | 65732.74 | 2025-02-01 | 2025-02-09 | Late Risk
P1003-PO007 | P1003 | P1003-T07 | Valley Civil | Structural | 131804.66 | 120379.94 | 2025-03-01 | 2025-02-27 | On Track
P1003-PO008 | P1003 | P1003-T08 | Mesa Steel | Structural | 137473.65 | 134861.68 | 2025-03-30 | 2025-04-11 | Late Risk
P1003-PO011 | P1003 | P1003-T11 | Desert Safety Supply | Mechanical | 115487.21 | 109720.14 | 2025-01-28 | 2025-02-05 | Late Risk
P1003-PO012 | P1003 | P1003-T12 | Mesa Steel | Mechanical | 114930.16 | 101932.17 | 2025-02-28 | 2025-03-06 | Late Risk
P1003-PO013 | P1003 | P1003-T13 | Copperline Electric | Mechanical | 116194.13 | 101383.8 | 2025-03-28 | 2025-03-25 | On Track
P1003-PO016 | P1003 | P1003-T16 | Copperline Electric | Electrical | 79878.88 | 66752.77 | 2025-02-02 | 2025-02-08 | Late Risk
P1003-PO017 | P1003 | P1003-T17 | Sonoran Controls | Electrical | 84109.49 | 80394.25 | 2025-03-04 | 2025-03-12 | Late Risk
P1003-PO018 | P1003 | P1003-T18 | Sonoran Controls | Electrical | 136886.5 | 107001.02 | 2025-03-26 | 2025-03-24 | On Track
P1003-PO021 | P1003 | P1003-T21 | Desert Safety Supply | Instrumentation | 150839.66 | 158904.13 | 2025-01-31 | 2025-02-03 | Late Risk
P1003-PO022 | P1003 | P1003-T22 | Mesa Steel | Instrumentation | 76117.23 | 69170.01 | 2025-03-05 | 2025-03-02 | On Track
P1003-PO023 | P1003 | P1003-T23 | Sonoran Controls | Instrumentation | 74328.95 | 77530.66 | 2025-04-05 | 2025-04-07 | Late Risk
P1003-PO026 | P1003 | P1003-T26 | Mesa Steel | Commissioning | 112480.92 | 94845.18 | 2025-02-02 | 2025-01-31 | On Track
P1003-PO027 | P1003 | P1003-T27 | Sonoran Controls | Commissioning | 80775.52 | 87378.48 | 2025-03-02 | 2025-02-28 | On Track
P1003-PO028 | P1003 | P1003-T28 | Desert Safety Supply | Commissioning | 71210.13 | 65067.7 | 2025-04-05 | 2025-04-04 | On Track
P1004-PO001 | P1004 | P1004-T01 | Valley Civil | Civil | 118730.52 | 89095.14 | 2025-03-22 | 2025-04-06 | Late Risk
P1004-PO002 | P1004 | P1004-T02 | Valley Civil | Civil | 112833.41 | 85333.04 | 2025-04-16 | 2025-04-24 | Late Risk
P1004-PO003 | P1004 | P1004-T03 | Desert Safety Supply | Civil | 105254.02 | 90099.32 | 2025-05-11 | 2025-05-12 | Late Risk
P1004-PO006 | P1004 | P1004-T06 | Desert Safety Supply | Structural | 77603.66 | 64301.38 | 2025-03-11 | 2025-03-12 | Late Risk
P1004-PO007 | P1004 | P1004-T07 | Desert Safety Supply | Structural | 97838.61 | 85897.89 | 2025-04-13 | 2025-04-18 | Late Risk
P1004-PO008 | P1004 | P1004-T08 | Desert Safety Supply | Structural | 148922.13 | 113658.17 | 2025-05-10 | 2025-05-11 | Late Risk
P1004-PO011 | P1004 | P1004-T11 | Desert Safety Supply | Mechanical | 52445.21 | 44681.6 | 2025-03-16 | 2025-03-21 | Late Risk
P1004-PO012 | P1004 | P1004-T12 | Desert Safety Supply | Mechanical | 65609.84 | 69136.9 | 2025-04-17 | 2025-04-19 | Late Risk
P1004-PO013 | P1004 | P1004-T13 | Valley Civil | Mechanical | 114341.59 | 91261.36 | 2025-05-14 | 2025-05-23 | Late Risk
P1004-PO016 | P1004 | P1004-T16 | Mesa Steel | Electrical | 205759.39 | 164812.21 | 2025-03-22 | 2025-04-02 | Late Risk
P1004-PO017 | P1004 | P1004-T17 | Copperline Electric | Electrical | 69330.68 | 62298 | 2025-04-14 | 2025-04-27 | Late Risk
P1004-PO018 | P1004 | P1004-T18 | Sonoran Controls | Electrical | 108592.38 | 101891.26 | 2025-05-17 | 2025-05-18 | Late Risk
P1004-PO021 | P1004 | P1004-T21 | Copperline Electric | Instrumentation | 78167.49 | 84079.24 | 2025-03-15 | 2025-03-22 | Late Risk
P1004-PO022 | P1004 | P1004-T22 | Apex Mechanical | Instrumentation | 113969.44 | 115295.59 | 2025-04-18 | 2025-04-18 | On Track
P1004-PO023 | P1004 | P1004-T23 | Copperline Electric | Instrumentation | 110444.45 | 97833.5 | 2025-05-09 | 2025-05-17 | Late Risk
P1004-PO026 | P1004 | P1004-T26 | Copperline Electric | Commissioning | 72820.21 | 64707.53 | 2025-03-14 | 2025-03-29 | Late Risk
P1004-PO027 | P1004 | P1004-T27 | Mesa Steel | Commissioning | 84477.34 | 72187.21 | 2025-04-13 | 2025-04-17 | Late Risk
P1004-PO028 | P1004 | P1004-T28 | Desert Safety Supply | Commissioning | 159677.53 | 172890.93 | 2025-05-08 | 2025-05-15 | Late Risk

## SQL_Practice
SQL Topic | Practice Query Goal | Why It Matters For This Role
SELECT and WHERE | Filter delayed schedule tasks | Find work packages needing attention
GROUP BY | Summarize cost by project and discipline | Build project status indicators
JOIN | Combine projects, cost, and schedule tables | Create integrated reporting
CASE | Create risk flags | Turn raw data into action labels
Views | Save a project status report query | Create reusable reporting logic
Export | Send SQL result to Excel or Power BI | Connect analysis to business users